## Slide 1: 167th C.P.W.D. Day
Central Public Works Department
12th July 2021
Technical Session

## Slide 2: Comparative Study of Contract Management System in CPWD, DMRC and NHAI and it’s relevance to CPWD

## Slide 3
  The study is based on:
    Structured recorded interview with the Senior Officers and Higher Management
    Detailed study of manuals, SOPs, agreements and documents available on website

## Slide 4: Presentation shall focus on:
Salient features of DMRC
Salient features of NHAI
Recommendation for CPWD

## Slide 5: SALIENT FEATURES IN DMRC’S PROJECT MANAGEMENT SYSTEM
1. 10% interest free mobilisation advance
There is a provision of giving 10% mobilisation advance to the agency on his request which is interest free. The recovery of this mobilisation advance starts after 20% of work is done and paid to contractor. This provision is a big assistance to the agency to ensure financial liquidity for speedy execution of work. At the same time, it provides contractor an opportunity to earn profit without investing money from his own account.

## Slide 6
2. Release of 80% amount of running account bill within 72 hours
On submission of the running account bill by the contractor, 80% of the amount is released within 72 hours only on preliminary checking. Detail checking of the bill and payment is done subsequently.
3. Availability of funds
Work is awarded to the contractor only if 100% funds is available with DMRC. Therefore, there is no hindrance in the work on account of non-availability of funds which is the case in most of the department. In DMRC no work suffers for want of funds.

## Slide 7
4. Compensation for suspension of work
This feature of G.C.C. provide considerable financial support to contractor in case of suspension of work by the department beyond period of 30 days. His financial position is not harmed due to idling of labour and machinery for which he is duly compensated with 15% extra as overheads and he still remains in position to deliver the project.
Further, if the work remain suspended for more than 90 days, contractor shall have right to ask for closure of the contract or deletion from the contract of that part of the work, which has been suspended.

## Slide 8
5. Payment of additional cost for unforeseeable physical condition
There is a (GCC Clause 4.23) provision for payment of additional cost for certain physical conditions which could not have been reasonably foreseen by an experienced contractor while quoting rates. The decision for the same shall be taken by the Engineer-in-charge. This is an additional assurance to the contractor for his liquidity. However, such unforeseeable physical condition have not been defined in the contract and it is left to the decision of the Engineer. This should be properly defined so that proper decision can be taken in this regards.

## Slide 9
Provision in NHAI (similar provision in CPWD)
Except as otherwise stated in the Agreement: (a) the Contractor accepts complete responsibility for having foreseen all difficulties and costs of successfully completing the Works; (b) the Contract Price shall not be adjusted to take account of any unforeseen difficulties or costs; and (c) the Scheduled Completion Date shall not be adjusted to take account of any unforeseen difficulties or costs.

## Slide 10
6. Focus on Delivery
The focus of DMRC always remain on timely delivery of the project. This play vital role while deciding various issues cropped up during the execution of the project. Decision are taken with primary focus on project delivery. The general feeling in DMRC is that the attitude of organization matters more than the rules. The grievances of contractors are also addressed in such a manner that it helps the project delivery on time.

## Slide 11
7. Dispute Resolution
The system of dispute resolution in DMRC includes provision of referring the grievances of contractors to Director Level Committee, which has powers to go even beyond the provisions of agreement and resolve the matter.

## Slide 12
8. 10% Performance Security
The amount of Performance Security is 10% in DMRC, whereas at other place it is only 5% (however, currently, it is reduced by Govt. to 3% due to COVID-19). Keeping such a large amount (10%) as performance security which is forfeited in case of default by the contractor is a big deterrent for a contractor to venture into the default.
9. Debarment Policy
The DMRC has a debarment policy which has provision to debar the contractor if any default is committed by him or any misrepresentation or false representation is made by him in tendering and on any other ground. This also acts as deterrent for the contractor against any default by him.

## Slide 13
10. Recovery of Liquidated Damages
System of recovery of liquidated damages is more reasonable in DMRC as the rate is already mentioned in contract milestone-wise. It is not left to the decision of a particular authority. At the same time, the maximum quantum of liquidated damages is 15% as against 10% in other departments

## Slide 14
11. Ease in tendering process
Documents of lowest bidders only verified
There is no marking system in deciding the eligibility bid
The completed works or on going work of the bidders are not inspected
b and c above reduces a lot of work in finalizing the eligibility bid and saves overall time and makes tendering system less prone to deputes.

## Slide 15
12. Effective Safety Monitoring
Four level Safety Monitoring System
Two from Department side
Site monitoring
HQ monitoring
Two from Contractors side
Site monitoring
HQ monitoring

## Slide 16: SALIENT POSITIVE FEATURES OF NHAI SYSTEM
1. Ease in Tendering Process
Documents not verified from issuing authority before deciding the eligibility bid unless there is some reason for doubt or complain.
There is no marking system in deciding the eligibility bid.
The eligible works or ongoing work of the bidders are not inspected.
This reduces a lot of work in finalizing the eligibility bid and saves overall time. However, this system has its own drawbacks also.

## Slide 17
2. Availability of funds
In NHAI, work is awarded only when the full funds are available. No work suffers for want of funds which is big positive factor.
3. 15% Mobilisation Advance
The provision of Mobilisation Advance in NHAI contracts is total 15% (including 5% Mobilisation Advance for equipment and machinery) whereas in CPWD and DMRC, Mobilisation Advance is only 10% (including 5% for equipment and machinery). The Mobilisation Advance in NHAI and CPWD is interest bearing whereas in DMRC, it is interest free. Facility for extra mobilisation advance in NHAI is a positive factor for progress of works. However, interest free mobilisation advance in DMRC is certainly much more a positive factor.

## Slide 18
4. Additional Performance Security for Low Rated Contract
If the quoted price of the contractor is lower than 10% but up to 20% of the estimated cost, Additional Performance Security shall be @ 20% of the tendered price below 10% of the estimated cost.
If the quoted price of the contractor is lower than 20% of the estimated cost, Additional Performance Security shall be @ 30% of the tendered price below 10% of the estimated cost.
This is more reasonable to link the quantum of Performance Security with the quoted rate of the contractor, if the quoted rate of the contractor is lower beyond a point.
More the performance security, better deterrent against contractual default by the contractor. Hence it’s an additional safeguard against contractors default.

## Slide 19
5. Damages for delay in handing over the site
As per the terms of contract, (Article 8.3), the Authority shall pay damages to the contractor in accordance with specified formula for the part of the site which has not been provided to the contractor up to the specified time. This shall induce extra caution in the department to hand over the site on time.
Amount of damages in Rs Per day per meter = 0.05 X C X 1/L X 1/N
Where, C = Contract Price, L = Length of the Project Highway in meter, N = Completion period in days.

## Slide 20
6. Deemed termination of Contract
As per article 3.4 of the contract, the contract shall be considered deemed terminated if due to any reasons, whatsoever, the appointed date does not occur within 90 days of signing of the agreement. In such event, the contractor shall be paid damages equivalent to 1% of the contract price.
Due to this provision, the department as well as the contractor shall work hard and make it absolutely certain to remove all hurdles and commence the work before the above date, failing which the contract shall automatically be terminated and both the parties shall be at loss.
“Appointed Date means the date declared by the authority as the project commencement date with the consent of the contractor as per the process specified in Article 3 & 2 of the agreement.”

## Slide 21
7. Debarment Policy
As per article-10.3(iv) of the contract (project above 300 crore ), if the contractor fails to complete the project within 90 days from the Schedule Completion Date unless such failure has occurred due to Force Majeure or reasons solely attributable to the Authority, the contractor shall be deemed to be ineligible for bidding future projects of the Authority. Hence it’s an additional deterrent for the contractor to delay the work beyond 90 days from the scheduled completion date.

## Slide 22
8. Dispute Resolution
For resolution of dispute, apart from provision of Conciliation and Arbitration, there is a provision of referring the dispute to Chairman of the Authority and the Chairman of the Board of Director of the Contractor for amicable settlement. This is expected to resolve the dispute and avoid arbitration

## Slide 23: Recommendation for CPWD

## Slide 24: Recommendation for CPWD
1. Ease in tendering system
Marking system of the eligible bid is a time consuming process. It is also observed that after fulfilling minimum eligibility criteria, most of the bidders get qualified in the evaluation process. Therefore, the marking system should be discontinued as in other organizations. This will save a lot of time and make tendering process easier. However, if required, a study of actual effect of marking system on eligibility bid can be conducted.
Similarly, hardly any bidder fails in quality on physical inspection of works (completed or ongoing). However, it consumes considerable time and effort. Therefore, for quality, client’s certificate in Form D should be relied upon and system of physical inspection of work should be discontinued as in other departments.
Since the bidding capacity calculation is dependent only on the declaration made by the contractor about the works in hand, it is not a very reliable system. Either some other more reliable system should be developed for calculating the bidding capacity or it should also be discontinued. A study of actual effect of bidding capacity criteria on eligibility bid can also be conducted.
Tendering process shall get easier, save lot of time and less prone to disputes.

## Slide 25
2. Provision of additional performance security
There should be provision of additional performance security for contracts priced below 10% of ECPT. For contracts priced below 20% of ECPT, rate of additional performance security should be even further higher rates.

## Slide 26
3. Compensation for suspension of work from department side
There should be provision in the G.C.C. to provide compensation to the contractor in case of suspension of work by the department beyond period of 30 days for idling of labour and machinery besides granting EOT.
By granting EOT, escalation becomes payable but the indices for calculation of 10CC are considered only up to the stipulated date of completion. Hence the contractor is not compensated even for the increase in prices of material and labour. Hence some compensation for idle labour and machinery is essentially required.
Further, if the work remain suspended for more than 90 days, contractor should have right to ask for closure of the contract or deletion from the contract of that part of the work, which has been suspended.

## Slide 27
4. Payment of additional cost for unforeseeable physical condition
For EPC contracts, there should be provision for payment of additional cost for certain physical conditions which could not have been reasonably foreseen by an experienced contractor while quoting rates. However such decision and the quantum of compensation should be approved by one authority above the PM or CPM.
5. Release of 80% amount of running account bill within 4 days
On submission of the running account bill by the contractor, 80% of the amount should be released within 4 days only on preliminary checking. Detail checking of the bill and payment should be done subsequently.

## Slide 28
6. Focus on Delivery
The focus of the organization should always remain on timely delivery of the project. This shall play a vital role while deciding various issues cropping up during the execution of the project. Decision should be taken keeping in view the interest of all stakeholders including a focus on project delivery. The attitude of organization matters more than the rules. The grievances of contractors should be addressed in such a manner that it helps the project delivery on time.
It should be considered to introduce such guidelines in the manual. This will favour bona fide decisions in favour of work.

## Slide 29
7. Debarment Provision in contracts
If the contractor fails to complete the project within specified days (to be specified in each contract) from the Schedule Completion Date unless such failure has occurred due to Force Majeure or reasons solely attributable to the department, the contractor shall be deemed to be ineligible for bidding future projects of the department for 2 year. It shall be an additional deterrent for the contractor against delaying the work beyond scheduled completion date.

## Slide 30
6. Deemed termination of contract
There should be provision in the EPC contracts that the contract shall be considered deemed terminated if due to any reasons, whatsoever, the physical commencement of the work does not occur within the “specified days” of signing of the agreement. The “specified days” should be decided case to case basis after giving due consideration to all preconstruction activities.
Due to this provision, the department as well as the contractor shall work hard and make it absolutely certain to remove all hurdles and commence the work before the above date, failing which the contract shall automatically be terminated and both the parties shall be at loss

## Slide 31
9. Safety Monitoring
There should be provision of regular safety inspection and safety audit at significant stages of the project. For this purpose, provision should be made for posting of a Safety Officer of the level of SE at each project region. Provision of third party safety inspection and safety audit may also be introduced.
Essential safety related items should be included in DSR and should be included in contract BOQ. This shall ensure due payments to the contractors and effective implementation of essential safety items in the work. Such items could be providing railings, nets, green covers etc.

## Slide 32
10. Dispute Resolution
For resolution of disputes, the matter should be referred to ADG level committee for reconciliation and resolution of disputes. The committee should have powers to go even beyond the provisions of agreement where such approach is logically required.

## Slide 33
Thanks